ADVERTISEMENT FOR BIDS
Subject to conditions prescribed by the University of California, San Francisco, sealed bids for a Long Form Lump Sum Contract are invited for the following Work:

MB Block 15 Interim Public Parking Project No.: PRJ-000591
UNIVERSITY OF CALIFORNIA, SAN FRANCISCO

DESCRIPTION OF WORK:
Provide all labor, materials, equipment, tools, transportation, and services required for construction of approximately 118,000 gross square feet of interim public parking improvements at UCSF Mission Bay Block 15, in accordance with current applicable codes and UCSF parking standards and requirements. Base Scope of Work includes site clearing and preparation; earthwork, grading, and drainage; paving and pavement striping; concrete curbs, sidewalks, and related site improvements; minor modifications to private streets; planting and landscape improvements; site electrical and lighting systems; UCPD blue-light emergency communication infrastructure; EV parking and charging infrastructure; traffic-control and parking equipment; associated security and low-voltage systems; and new, modified, or relocated utilities necessary for a complete and operational public parking facility.
The Work shall be phased and sequenced to maintain University operations and provide beneficial use of the northern approximately 50 percent of Block 15 (PHASE 1 AREA) for University parking and construction laydown no later than November 1, 2026. During Phase 1, the University will continue to occupy portions of the northern area. University-stored items and operations will be relocated within Block 15, as practicable, to mutually agreeable locations to permit completion of the required Work.
This Project is divided into three (3) Phases.

Phase 1 consists of: Complete major intrusive Work within the PHASE 1 AREA sufficiently in advance of the November 1, 2026 turnover to permit safe and practical exclusive use of the designated area by the University for parking and laydown. Major intrusive Work includes, but is not limited to, underground utilities and raceways, trenching, backfill, paving, concrete foundations and equipment bases, and other Work that would materially interfere with University use. Following turnover, only minor Work that can be safely performed without materially interfering with University operations may remain within the occupied area. Such Work, including wire pulling, installation or erection of site-lighting equipment, testing, and similar activities, shall be performed only with advance University approval and coordination and may require off-hours or weekend Work.

Phase 2 consists of: Following turnover of the PHASE 1 AREA, complete all remaining Base Scope of Work within the stipulated Contract Time while maintaining University access and operations within occupied portions of Block 15 with the exception of the installation of EV Charging Stations. Coordinate Work affecting occupied areas with the University in advance.
Phase 3 consists of: Installation of EV Charging Stations
UNIVERSITY OF CALIFORNIA, SAN FRANCISCO
Project No.: PRJ-000591
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BIDDER QUALIFICATIONS:

Contractor: To be eligible for consideration for award, bidders must have the minimum experience of successfully completing at least two (2) comparable projects, with a construction contract amount of $1,000,000 or greater within the last ten (10) years of the bid opening date.
PROCEDURES:
Bidding Documents will be available to Bidders on September 11, 2026 on BuildingConnected. Visit the University of California Public Plan Room at https://app.buildingconnected.com/public/654ab4b90da0a10035053c78

A mandatory Pre-Bid Conference and mandatory Pre-Bid Job Walk will be conducted on September 17, 2026 beginning promptly at 10:00 AM. Participants shall meet at UCSF Mission Bay - Block 15, 750 Nelson Rising Lane San Francisco, CA 94158. Only bidders who participate in both the Conference and the Job Walk in their entirety will be allowed to bid on the Project as prime contractors. For further information, contact University's Project Manager, Ted Meyer at 415-290-6095.
The Electrical Contractors are recommended to attend the mandatory Pre-Bid Conference and Pre-Bid Job Walk.

To be allowed to submit a bid, Bidders must have the minimum experience set forth in the Contractor’s Statement of Experience (Exhibit 24). Bidders must fill out the aforementioned Contractor’s Statement of Experience (Exhibit 24) and submit it by September 22, 2026, 2:00 PM and will only be received using Building Connected. Use the “Messages” tab to attach. Submit with a message subject of “Contractor’s Statement of Experience – Company Name.”
Bidders will be notified whether or not they are allowed to submit a bid for this project within five (5) business days of the due date of the Contractor’s Statement of Experience (Exhibit 24).

If you have any issues using BuildingConnected, go to their support hub and click the '?' symbol at the bottom left corner to access their Knowledge Base, initiate a live chat, or send a message to the BuildingConnected team.

Every effort will be made to ensure that all persons have equal access to contracts and other business opportunities with the University within the limits imposed by law or University policy. Each Bidder may be required to show evidence of its equal employment opportunity policy. The successful Bidder and its subcontractors will be required to follow the nondiscrimination requirements set forth in the Bidding Documents and to pay prevailing wage at the location of the work.
In addition, the University is committed to promoting and increasing participation of small business enterprises (SBEs) and disabled veteran business enterprises (DVBEs) relating to all goods and services covered under the awarded agreement, subject to any and all applicable obligations under state and federal law, and University policies. The awarded contractor shall make best efforts to provide qualified SBEs and DVBEs with the maximum opportunity to participate. Please contact REOutreach@ucsf.edu for further information.

The work described in the contract is a public work subject to section 1771 of the California Labor Code.
No contractor or subcontractor, regardless of tier, may be listed on a Bid for, or engage in the performance of any portion of this project unless registered with the Department of Industrial Relations pursuant to Labor Code section 1725.5 and 1771.1.


This project is subject to compliance monitoring and enforcement by the Department of Industrial Relations.


REGISTER AT THIS LINK: https://services.dir.ca.gov/gsp [The contractor registration link is on the right side.]
The successful Bidder shall pay all persons providing construction services and/or any labor on site, including any University location, no less than the highest of UC Fair Wage; California Minimum wage; and Local minimum wage; and shall comply with all applicable federal, state and local working condition requirements

The successful Bidder will be required to have the following California current and active contractor’s license at the time of submission of the Bid:

	LICENSE CLASSIFICATION:
	General Building

	LICENSE CODE:
	B


ESTIMATED CONSTRUCTION COST: $ 3,000,000 THE REGENTS OF THE UNIVERSITY OF CALIFORNIA
University of California, San Francisco September, 2026
